## WBS
Estimation for design and development
Project Name: "Flickr Search"
Date: 26-Aug-2016
Platform: iOS 8.0 onwards
Supporting Devices: iPhone 6 onwards
Orientation: Portrait
* All estimations are in person minutes
S No. | Tasks | Person Minutes | Remarks
Setup & Design
1 | Project Planning & Sprint creation | 40
2 | Study Flickr API & Account creation | 60
3 | Project and repository setup | 40
Development Phase
4 | Data manager for API calls | 30 | Backend
5 | Shared Class Configuration | 30 | Backend
6 | Validation | 50 | Backend
7 | Dashboard Navigation | 150 | Functional Requirement
8 | Detail page navigation | 30 | Functional Requirement
9 | Detail page swipe transition | 90 | Functional Requirement
10 | Detail page photo description | 60 | Functional Requirement
11 | Detail page tap to hide menu | 30 | Non-Functional Requirement
12 | Hide search on scroll | 40 | Non-Functional Requirement
13 | Display top images on load | 30 | Non-Functional Requirement
14 | 3D Force Touch to preview | 50 | Non-Functional Requirement
15 | Tap to save image locally | 60 | Non-Functional Requirement
16 | Maintain recent search | 60 | Non-Functional Requirement
17 | Share option through share-sheet | 30 | Non-Functional Requirement
Development Minutes |  | 880
Code Review
18 | Code review | 30
Documentation
19 | AppleDoc Formatted | 30 | On going activity when creating methods
Apple's iTunes Release Activity
20 | Application submittion to iTunes |  | (Optional) Subjected to Apple's review and publish policy
Grand Total | Minutes | 940
| Hours | 15.6667

## SPRINTS
SPRINTS
Project Name: "Flickr Search"
Date: 26-Aug-2016
Platform: iOS 8.0 onwards
Supporting Devices: iPhone 6 onwards
Orientation: Portrait
S No. | Backlog | Sprint Number | Build Number | Priority | Owner | Acceptance Criteria | Start Date | End Date | Status | Release Date
1 | Project setup & class creation | 1 | 1 | 5 | Praveen Topno | Successful compilation | 2016-08-26 | 2016-08-26 | COMPLETED | 2016-08-26
2 | Data manager for API calls | 1 | 1 | 10 | Praveen Topno | Send request and receive response | 2016-08-26 | 2016-08-26 | COMPLETED | 2016-08-26
3 | Shared Class | 1 | 1 | 15 | Praveen Topno | Check global ivars are accessible | 2016-08-26 | 2016-08-26 | COMPLETED | 2016-08-26
4 | Validation | 1 | 1 | 20 | Praveen Topno | Search string validation, flikr should not throw error | 2016-08-26 | 2016-08-26 | COMPLETED | 2016-08-26
5 | Crash handler | 1 | 1 | 25 | Praveen Topno | Try-catch in data processing | 2016-08-26 | 2016-08-26 | COMPLETED | 2016-08-26
6 | Dashboard Navigation | 2 | 2 | 5 | Praveen Topno | UI View and delegate implementation | 2016-08-27 | 2016-08-27 | COMPLETED | 2016-08-27
7 | Collection view implementation | 2 | 2 | 10 | Praveen Topno | Collection view layout | 2016-08-27 | 2016-08-27 | COMPLETED | 2016-08-27
8 | Detail page navigation | 2 | 2 | 15 | Praveen Topno | Navigation link between Dashboard & Details | 2016-08-27 | 2016-08-27 | COMPLETED | 2016-08-27
9 | Detail page swipe transition | 2 | 2 | 20 | Praveen Topno | Must be swipable and load images in detail view | 2016-08-27 | 2016-08-27 | COMPLETED | 2016-08-27
10 | Detail page photo description | 2 | 2 | 25 | Praveen Topno | Photo title in details | 2016-08-27 | 2016-08-27 | COMPLETED | 2016-08-27
Features & Non-Functional Requirements
15 | Cancellable search | 3 | 3 | 5 | Praveen Topno | If one search is queued and new search is requested, then cancel previous search and downloads | 2016-08-27 | 2016-08-27 | COMPLETED | 2016-08-27
13 | Dashboard color theme change after search | 3 | 3 | 10 | Praveen Topno | Initially light grey then dark background of collectionview | 2016-08-27 | 2016-08-27 | COMPLETED | 2016-08-27
12 | Dashboard Add child view controller for help/info | 3 | 3 | 15 | Praveen Topno | For easy maintenance of info updates | 2016-08-27 | 2016-08-27 | COMPLETED | 2016-08-27
14 | Dashboard help info with user defaults | 3 | 3 | 20 | Praveen Topno | Hide help after some time, maintain status with NSUserDefaults | 2016-08-27 | 2016-08-27 | COMPLETED | 2016-08-27
COMPLETED
20 | Details Header will show Title of image | 4 | 4 | 5 | Praveen Topno | Title must change with each image swipe change | 2016-08-28 | 2016-08-28 | COMPLETED | 2016-08-28
26 | Swipe to change image download if not done already | 4 | 4 | 10 | Praveen Topno | If image is not downloaded in dashboard, then download and show | 2016-08-28 | 2016-08-28 | COMPLETED | 2016-08-28
19 | Detail view with Header/Footer using child view controller | 4 | 4 | 15 | Praveen Topno | Use Childviewcontroller for displaying header/footer | 2016-08-28 | 2016-08-28 | COMPLETED | 2016-08-28
25 | Swipe up gesture to dismiss view | 4 | 4 | 20 | Praveen Topno | User experience, swipe up to dismiss or tap close at top right corner | 2016-08-28 | 2016-08-28 | COMPLETED | 2016-08-28
24 | tap to make full screen | 4 | 4 | 25 | Praveen Topno | Fullscreen will hide header and footer leaving only image on screen | 2016-08-28 | 2016-08-28 | COMPLETED | 2016-08-28
21 | Footer will contain child view controller | 4 | 4 | 30 | Praveen Topno | footer | 2016-08-28 | 2016-08-28 | COMPLETED | 2016-08-28
22 | Footer will have save image button | 4 | 4 | 35 | Praveen Topno | Must ask user permission to access Photos and save | 2016-08-28 | 2016-08-28 | COMPLETED | 2016-08-28
23 | Footer will have share image through action sheet | 4 | 4 | 40 | Praveen Topno | Share image with actionsheet | 2016-08-28 | 2016-08-28 | COMPLETED | 2016-08-28
[7 empty] | 2016-08-28 | 2016-08-28 |  | 2016-08-28
16 | Popular image search | 5 | 5 | 5 | Praveen Topno | Use different Flickr API to search popular photos | 2016-08-28 | 2016-08-28 | COMPLETED | 2016-08-28
17 | If popular image searched clean user search data | 5 | 5 | 10 | Praveen Topno | User experience | 2016-08-28 | 2016-08-28 | COMPLETED | 2016-08-28
18 | Pull down to load popular photos, each pull brings fresh photo set | 5 | 5 | 15 | Praveen Topno | User experience | 2016-08-28 | 2016-08-28 | COMPLETED | 2016-08-28
11 | iOS 9 Force touch implementation for peek and pop | 5 | 5 | 20 | Praveen Topno | User experience | 2016-08-28 | 2016-08-28 | COMPLETED | 2016-08-28
12 | Search history | 5 | 5 | 25 | Praveen Topno | User experience | 2016-08-28 | 2016-08-28
Release Activities:
13 | Integration and Release | 5 | 5 | 0 | Praveen Topno | Release Activity | 2016-08-29 | 2016-08-29 | COMPLETED | 2016-08-29

## Release Notes
Release Notes
Project Name: "Flickr Search"
Date: 26-Aug-2016
Platform: iOS 8.0 onwards
Supporting Devices: iPhone 6 onwards
Orientation: Portrait
S No. | Features | Build Number | Remarks
1 | Navigate in app | 1
2 | Search with Flickr API | 2
3 | View photos | 2
4 | Detailed view of photos | 2
5 | Integration of functional features | 2
6 | User experience | 3
7 | Search user experience | 3
8 | Dashboard user experience | 3
9 | Detailed view user experience | 4
10 | Popular search | 5
11 | Force touch | 5
12 | Search History | 5

## Limitations
Known Limitations
Project Name: "Flickr Search"
Date: 26-Aug-2016
Platform: iOS 8.0 onwards
Supporting Devices: iPhone 6 onwards
Orientation: Portrait
S No. | Description | Build Number | IS FIXABLE
1 | In detailed view app will not fetch next page images. Next page only can be fetched by dashboard. | 1 | YES
2 | Details page Zoom is disabled | 4 | YES
3 | Detail page info button at bottom has static comments | 4 | YES

## VERSIONS
Document Version History
S. No | Change Description / Change Request No | Changed By | Date | Approved By | Current Version | Next Version
1 | Initial Version | Praveen Topno | 2016-08-26 |  | 1 | 1.1

## Macros (hidden)
Macro For Sprint Status
OEPN
IN PROGRESS
COMPLETED
CLOSED